## List1
Timeline
Activity name | Terms (from–to)
Announcement of the call for submission of Return Grant applications | 1.12.2025
Deadline for submission of Return Grant applications at the CZU | 31.1.2026
Evaluation of submittted applications | 1.2.2026 - 31.3.2026
Publication of the results of the CZU Return Grant competition | 2026-03-31
Preparation of contracts between the CZU and the main researcher of the Return Grant and team members, including obtaining the required signatures | 1.4. - 30.4.2026
Expected start date of the implementation of funded Return Grants at the CZU | od 1.5.2026
Implementation of the supported Return Grants, ongoing monitoring, and evaluation of Interim Activity Reports | 1.5.2026 - 30.4.2029
Implementation of the supported Return Grants, ongoing monitoring, and evaluation of Interim Activity Reports | untill 30.4.2029